## Slide 1: Line Of Balance
Dr. Ahmed Elyamany

## Slide 2: Intended Learning Outcomes
Define the principles of Line of Balance
Demonstrate the application of LOB
Understand the importance of LOB
Understand the process of applying LOB

## Slide 3: Line of Balance (LOB)
Definition
  A simple diagram to show location and time at which a certain crew will be working on a given operation.
Focuses on balancing the time taken for individual activities by either re-distribution of resource or by reducing process waste.

## Slide 4: Line of Balance (LOB)
LOB is a Planning methodology to optimize resources used
LOB is a Good Visual tool that lets us see if a construction program can be achieved with the minimum waiting time between tasks
It is primarily used on projects that have repeated elements like Highways, Pipelines, High-rise buildings, hotel bedrooms, bridge etc.

## Slide 5: Benefits of LOB
Continuous resource use
Less starts and stops
Crews will spend less time and money on later units once they develop a learning momentum.
Improve productivity by 20 %
Save money and time
Faster planning process
Superior Visual control

## Slide 6: Faster planning process
Less tasks
Less links
Faster program creation
Less time to understand & interpret
Easy to try ‘what-if’ scenarios

## Slide 7: Activity-based vs. Location-based
Activity-based
  30 floors, 4 activities in each location = 120 activities
  Formwork-reinforcement-pouring on the same floor = 60 links
  Pouring – formwork next floor = 29 links
  Pouring – finishes two floors below = 28 links
  Internal links in finishes to prevent resource overlapping = 29 links
  Total: 120 CPM activities, 266 links
Location-based
  4 tasks flowing through locations
  4 links between activities
  4 links inside activities
  Total: 4 tasks, 8 link

## Slide 8: Activity-based
Formwork
Floor 1
Reinforcement
Floor 1
Pouring Conc.
Floor 1
Finishing
Floor 1
Formwork
Floor 2
Reinforcement
Floor 2
Pouring Conc.
Floor 2
Finishing
Floor 2
Formwork
Floor 3
Reinforcement
Floor 3
Pouring Conc.
Floor 3
Finishing
Floor 3

## Slide 9: Location-based
Pouring Conc.
Reinforcement
Time
Units
3
2
1
30
.
.
.
.
Formwork
Finishing

## Slide 10: Superior project control
Easy to interpret
Clear uncomplicated displays
Simple to manage
Easy to monitor
Effortless progress updates
Effective control

## Slide 11: LOB Calculations
The objective of using LOB is to achieve a resource-balanced schedule by determining the suitable crew size and number of crews to employ in each repetitive activity.
This is done such that:
  the units are delivered with a rate that meets a pre-specified deadline
  the logical CPM network of each unit is respected
  crews’ work continuity is maintained.
The analysis also involves determining the start and finish times of all activities in all units and the crews’ assignments.

## Slide 12: Three diagrams are used in LOB
1. Production Diagram
  Shows the relationships of the activities for a single unit.
2. Objective Diagram
  Used to plot the planned or actual number of units produced vs. time.
3. Progress Diagram
  Shows the number of units for which the activity has completed .

## Slide 13: Drawing the LOB Schedule
Similar rates  parallel lines
Different rates  lines not parallel
Conflict points  at the last or first unit
R= (n – 1)/(tf – t0)
Time
Units
n
.
.
.
.
.
.
1
n - 1
t0
tf
R
tf

## Slide 14: LOB Calculations
The CPM-LOB formulation involve:
  Crew synchronization
  Calculating resource needs
  Drawing the LOB schedule

## Slide 15: Crew Synchronization
A simple relationship between the duration taken by a crew in one unit (D) and the number of crews (C) to employ in a repetitive activity
Slope of the shaded triangle in becomes:
R = 1 / (D / C)
Then: C = D x R
Crew 3
R
Crew 1
Crew 2
R
Time
Units
3
2
1
1
2
3
0
D/C
D/C
D/C

## Slide 16: Calculating Resource Needs
B
Time
Units
n
.
.
.
2
1
A
D
C
n - 1
C(2)
B(5)
D(5)
A(5)
TF=3
Ri = (n – 1) / (TL - T1) + TFi
Ci = Di x Ri
Cai = Round Up (Ci)
Rai = Cai / Di
C(2)
B(5)
D(5)
A(5)
TF=3
C
C

## Slide 17: Example
A |  | 
B |  | 
C |  | 
D |  | 
E |  | 
N=61 units
Required ; draw LOB at month 16
Activity | A | B | C | D | E
Production rate | 3 | 5 | 5 | 3 | 1
No of crews | 9 | 30 | 10 | 9 | 2

## Slide 18: Example
R = 1 / (D / C)
D = C/R
Activity | A | B | C | D | E
Production rate | 3 | 5 | 5 | 3 | 1
No of crews | 9 | 30 | 10 | 9 | 2
Duration | 3 | 6 | 2 | 3 | 2
0 |  | 3
A |  | 
3 | 3 | 6
0 |  | 6
B |  | 
0 | 6 | 6
6 |  | 8
C |  | 
6 | 2 | 8
8 |  | 11
D |  | 
8 | 3 | 11
11 |  | 13
E |  | 
11 | 2 | 13
0 |  | 0
Start |  | 
0 | 0 | 0

## Slide 19: Example
For A: R=3, t0=3,
Time
Units
61
.
.
.
.
.
.
.
1
tf=3+(61-1)/3=23
For B: R=5, t0=6,
tf=6+(61-1)/5=18
For C: RC=RB>RA, buffer from top
t0=25-(61-1)/5=13
R=5, tf=23+2=25,
B
C
For D: R=3, t0=13+3=16,
tf=16+(61-1)/3=36
For D: R=1, t0=16+2=18,
tf=18+(61-1)/1=78
0 10 20 30 40 50 60 70 80
D
E
18
3
6
13
16
18
23
25
36
78
A

## Slide 20: Example
Time
Units
For A: R=3, t0=3,
16=3+(x -1)/3, x=40
For B: R=5, t0=6,
16=6+(x -1)/5, x=51
For C: R=5, t0=13,
16=13+(x -1)/5, x=16
For D: R=3, t0=16,
For E: x=0
A B C D E
40
51
16
1
0
B
C
D
E
A
16=16+(x -1)/3, x=1
Progress Diagram
Objective Diagram
20
30
28
Actual
Planned

## Slide 21: Example
B
C
D
E
A

## Slide 22: Questions
Contact:
Dr. Ahmed Elyamany
019-4100-824
a2hyamany@yahoo.com