## Slide 1: Analysis of Alternatives (AoA) for ACAT II and ACAT III Programs
Mr. Howard Marks
ASC/AQ
24 Apr 12

## Slide 2: Objective
Familiarize attendees with:
  Requirements for conducting AoAs
  Desirability of accomplishing AoAs on smaller programs, especially platform mods
  Other AoA uses
    Technology alternatives
    Materiel solutions
  The new ASC Tailored AoA process
    Designed to be user friendly!

## Slide 3: Requirements for an AoA
Public Law, DoDI 5000.02, AFI 63-101, and AFI 10-601 require all acquisition programs and potential programs to conduct an Analysis of Alternatives (AoA)
  May be waived by the MDA
ACAT I and retained-MDA ACAT II programs will use OSD and SAF/AQ guidance for approval of AoAs
ACAT III and Delegated-MDA ACAT II programs may use a tailored approach
  The PEO as MDA controls the process with using command coordination
  Should be a collaborative effort between SPO and user
  Contains an avenue for objective, third party input (the CAAT*)
  Again, the process is streamlined to enable results in weeks instead of months or years!
  * CAAT = Center AoA Advisory Team

## Slide 4: Background
Original “Big AoA” process
  Intended for MDAPs
  Not within the acquisition community’s control
    Owned by the using command
  Objectivity “encouraged” by mandatory PARCA involvement
  Accomplished by the Office of Aerospace Studies
The new, “Tailored AoA” process
  Documented in Chapter P11 of the ASC Process Guide Book
    Will be added to the new AFLCMC* Process Guidebook
  Process owned by ASC/AQ, co-owned by ASC/XR
  It’s streamlined!
  Mostly local participation
  User-friendly (e. g. PEO in control)!
  * AFLCMC = Air Force Life Cycle Management Center

## Slide 5: How the ASC Tailored AoA Process is Streamlined
Decision-making is local (e. g., PEO as MDA)
The “Big AoA” Study Guidance and AoA Study Plan are combined into a single document (The AoA Implementation Plan, or AIP)
  Approved by PEO as MDA
A local advisory group is used (the Center AoA Advisory Team, or CAAT)
AoA team membership is closer to home
The final report can be a briefing to the MDA

## Slide 6: When to Use the Tailored AoA Process
Can be used to evaluate any number of alternatives involving cost, performance, and time
Can evaluate
  Materiel solution candidates
  Technology alternatives
  Other courses of action
Can also evaluate based on supportability, risk, feasibility, technical/technology maturity, degree of development/nonrecurring effort required

## Slide 7: AoA Team Membership
Depends on the effort being analyzed and MDA direction
Chair: Program Manager (the “Study Director”)
  Or as otherwise directed by the MDA
Members
  Engineering
  Cost estimating
  Financial mgt
  Scheduler
  Life cycle logistician
  Risk manager
  Using command representative
  Others as needed
Team composition not mandatory -- members recruited as required

## Slide 8: Center AoA Advisory Team (CAAT) Membership
Chair: Should be ASC/XR
ASC/AQ
ACE
ASC/XR2
ASC/EN
ASC/FM
ASC/AQY (Life Cycle Logistics)
ASC/AQT (Center Test Authority) – if appropriate
Lead MAJCOM representative
The CAAT functions similar to the Senior Acquisition Team (SAT)

## Slide 9: AoA Implementation Plan
Combines requirements of two documents
  AoA Study Guidance, and
  AoA Study Plan
Contains the AoA schedule
Approved by the MDA
Contains
  Study parameters
  Mission needs/requirements
  Measures of effectiveness/performance
  Evaluation and ranking criteria for advance approval
    e. g., the decision matrix rows and columns
  How cost estimate, risk assessment, and schedule will be accomplished
  AFROC Coordination or waiver thereof
Requires using command coordination
Becomes blueprint for conduct of the AoA and final decision-making and reporting process

## Slide 10: How to Address the AoA at an MDD Event
Any ACAT program MDD needs to address the need for/intent to accomplish an AoA
  Present a plan to accomplish an AoA, or
  Provide rationale if one is not planned
Make sure that the ADM documents the final decision and captures the rationale
  MDA (PEO) signs

## Slide 11: Top-Level Tailored AoA Process Flow
Determine need for AoA and develop rationale
Conduct MDD, make AoA decision
Document “Yes” decision in ADM
Document “No” decision in ADM
No
Yes
Done
Finalize AoA Implementation Plan (AIP)
MDA Sign AIP
Conduct AoA
Coordinate with CAAT (and AFROC, if required)
Brief MDA
MDA select alternative
MDA approve alternative in ADM
Continue with acquisition process
Continue with acquisition process
ICD or CDD
Other inputs

## Slide 12: Sample AoA Decision Matrix
= All KPP thresholds met; meets/exceeds required schedule; low risk
= Most KPP thresholds met; close to meeting required schedule; moderate risk
Less than half of KPP thresholds met; not close to required schedule; high risk

## Slide 13: Training
Recommend the AoA team obtain initial/refresher training in the AoA process before starting out
There are several sources for this training and support
  Office of Aerospace Studies (preferred)
    Officially Air Force Materiel Command (AFMC) OAS/A9
    1655 1st Street SE, Kirtland AFB, NM 87117-5522
    505-846-8322, DSN 246-8322
    www.oas.kirtland.af.mil
  https://afkm.wpafb.af.mil/community/views/home.aspx?Filter=25628
  Defense Acquisition University (DAU)
    CLM101 (http://icatalog.dau.mil/onlinecatalog/courses.aspx?crs_id=243)
  The ASC ACE 937-255-5494, DSN 785-5494

## Slide 14: References
Joint Capabilities Integration and Development System (JCIDS)
  CJCSI 3170.01D – JCIDS
  CBA User’s Guide
DOD Acquisition Process
  DODD 5000.01 – The Defense Acquisition System
  DODI 5000.02 – Operation of the Defense Acquisition System
Air Force Specific Implementation
  AFI 10-601 - OPERATIONAL CAPABILITY REQUIREMENTS DEVELOPMENT
  AFI 63-101 - ACQUISITION AND SUSTAINMENT LIFE CYCLE MANAGEMENT
Office of Aerospace Studies (OAS) Handbooks
  OAS AoA Handbook
  OAS Pre-MDD Analysis Handbook
  Note: See OAS CoP for latest Handbooks (URL provided on previous slide)
ASC/XR may be contacted for advice and counsel

## Slide 15: Thank You!!
Any Final Questions?