## Instruction Sheet
TRL & MRL Rationale & Maturity Planning Worksheet Template
MRL Matrix Version 11: May 1, 2011
| Notes: | (1) Do not delete or move any row or column in any worksheet or the workbook will not perform correctly
(2) Input to the light blue shaded cells only, all other calculations, summaries, assessments, etc are auto-generated by the worksheets
(3) Tailoring out any of the following instructions may compromise fidelity of the Technology Readiness Assessment & Manufacturing Readiness Assessment (T&MRA)
Technology Readiness Assessment & Manufacturing Readiness Assessment (T&MRA) Process Steps
1 | Establish & align T&MRA Evaluation Team
| 1a | Establish cross functional team including engineering, manufacturing, program management, quality, and supply chain at a minimum…add additional functional areas as needed
| 1b | Align team on purpose, goals, processes, outputs, etc. of T&MRA
| 1c | Select the program's current phase of the product's life cycle (Materials Solution Analysis, Technology Development, EMD, LRIP, FRP); use pull-down menu on "T&MRA Information Sheet"
| 1d | Identify the system "products" (i.e. subsystem) that contain the key technologies to be assessed. Example: Missile Seeker
| 1e | Populate the "T&MRA Information Sheet" with the Program and Product (Sub-Assembly) to be assessed
2 | Identify Critical Technology Elements (CTE) and Key Manufacturing Technologies (KMT) to be Assessed
| 2a | Technology components &/or manufacturing processes essential to the systems performance which are new, novel or are being applied in a new or novel way. Technologies may be deemed a CTE or KMT in terms of system performance, affordability, manufacturing processes, materials, cost, risk, cycle time, rates/yields, maturity, infrastructure, etc.
| 2b | Critical Technology Elements are typically determined to be at the component level of a product or subsystem rather than the subsystem itself. Key Manufacturing Technologies, including processes, are separate from CTEs, such as a new Resin Transfer Mold system, or a new type of test station and equipment that is new or novel and poses significant risk to the manufacture of a CTE or subsystem.
| 2c | Example: Potential CTEs for a Seeker product (sub-assembly) might be: RF processor, antenna, gimbal, servo electronics, IR sensor, dome, etc. If any one or more of these technologies is determined by the assessment team to impose significant risk to the Seeker's manufacturability/affordability/performance, it is deemed to be a CTE which will require assessments of the CTE's TRL, MRL, and development of maturity plans to achieve readiness levels required for successful transition to the next program phase.
| 2d | Copy, Paste and Rename a new "T&MRL Assessment" and "Maturity Plan" worksheet for each CTE/KMT to be assessed (Example: Seeker Dome T&MRA and Seeker Dome Maturity Plan)
| 2e | Notify subcontractors who will need to be involved in assessments. Determine and negotiate best approach to deploy with subcontractor. Train &/or guide subcontractor team on TRA & MRA process and tools as required for accurate T&MRA.
3 | Establish Baseline Technology Readiness Levels
| 3a | Reference DoD's current state of Technology Readiness Guidance materials to determine TRL level criteria, descriptions and required supporting information.
| 3b | 2004 TRL Criteria and descriptions are included in separate worksheets within this workbook for reference (recommend assessment teams research for any updates to this criteria).
| 3c | Populate each "T&MRL Assessment" and "Maturity Plan" worksheets with the TRLs and justification/rationale for each
4 | Assess Each Technology's TRL Transition Readiness
| 4a | Reference DoD Acquisition Milestone Decision requirements & business best practices
| 4b | Recommended TRL levels for successful transition into: EMD = 6; LRIP = 7; FRP = 8.
| 4c | Note: The worksheets automatically assess transition readiness risk (red, yellow, green) based on the current phase of product life cycle you selected in the "T&MRA Information Sheet"
5 | Prepare Technology Readiness Maturity Plan
| 5a | Populate the "Maturity Plans" worksheet with detailed action plans (with rationale/evidence/risks to complete) to mature the current TRL to the desired level for program success
| 5b | Include estimated completion dates, responsible point of contact, funding requirements, how effort will be funded, etc. required by planning worksheets
| 5c | Evaluate for inclusion to Risk Management Systems such as "Risk Register"
6 | Establish Baseline Manufacturing Readiness Levels
| 6a | Reference DoD's "MRL Matrix" (included in this workbook) and/or "MRL Assist" tool, both can be found on DoDMRL.com website
| 6b | These tools will guide the collection of appropriate facts, data and artifacts that need to be analyzed for each CTE/KMT in order to establish justifiable MRLs
| 6c | Cross functional assessment team to determine MRL level for each of the relevant MRL Threads and Sub-threads; capture input from functional SMEs to avoid guesses & assumptions.
| 6d | Option: When assessing a CTE's MRL for the Manufacturing Process Maturity subthread, consider using the "Mfg'g Process Maturity" worksheet to show process details for any individual KMTs that pose unique & significant risk to the manufacture of the CTE being assessed.
| 6e | Log all baseline MRL data into each of the "T&MRL Assessment" and "Maturity Plan" worksheets
7 | Assess Each Critical & Key Technology's MRL Transition Readiness (Design & Manufacturability)
| 7a | Note: Each worksheet automatically assesses transition readiness risk (red, yellow, green) based on the phase of product life cycle you selected in the "T&MRA Information Sheet"
8 | Prepare Manufacturing Readiness Maturity Plan
| 8a | Populate the "Maturity Plan" worksheet with detailed action plans (with rationale/evidence/risks to completion) required to mature the current MRLs to the desired level for program success.
| 8b | Include estimated completion dates, responsible point of contact, funding requirements, how effort will be funded, etc. required by planning worksheets
| 8c | Evaluate for inclusion to Risk Management Systems such as "Risk Register"
9 | Conduct Regularly Scheduled T&MR Maturity Plan Reviews
| 9a | Periodically review with all key stakeholders during the life of the program
| 9b | Include T&MR discussions, status, risks, requirements, changes, etc. in all Gate Reviews
10 | Capture T&MRA Lessons Learned for Knowledge Management Purposes
| 10a | Document key lessons learned, provide to all T&MR process owners.

## T&MRA Information Sheet
1 | Program Name: |  | example: HyperSonic Missile Program
2 | Product (Subsystem level) |  | example: Missile Seeker
3 | Responsible POC(s):
|  | Position | POC | Phone #
|  | x | x | (xxx) xxx-xxxx
|  | x | x | (xxx) xxx-xxxx
|  | x | x | (xxx) xxx-xxxx
4 | Phase of Product Development:
5 | T&MRA Valuation Method
|  | List 5 | 2
Gate 2 Win Strategy Review
Gate 3 Pre-Proposal Readiness Review
Gate 4 Proposal Review
Gate 5 Planning & Control
Gate 6 Req'mts & Architecture Dev
Gate 7 Prelim Design Review
Gate 8 Critical Design Review
Gate 9 System Readiness Review
Gate 10 Production Readiness Review
|  | List 7 | 2
Material Solution Analysis
Technology Development
Engineering & Manufacturing Development
Production & Deployment
|  | List 8 | 1
Lowest T&MRL Values
Average T&MRL Values
Special Instructions:
- Input to Blue shaded cells only
- Do not move or delete any rows, columns or cells
or this workbook will not work properly.
- Input appropriate Program and Product being assessed…this
sheet will transfer this information to subsequent spreadsheets
- Pull-down menus provided below for items #4 "Phase of Product
Development" and #5 "T&MRA Valuation Method"

## T&MRL Assessment
Single T&MRA by MRL Matrix Threads
Program: |  |  | example: HyperSonic Missile Program
Product Description: |  |  | example: Missile Seeker
Product Development Phase: |  |  | Technology Development
Transition Readiness Goals: |  |  | 6
T&MRL Valuation Method: |  |  | Lowest T&MRL Values
Most Recent Assessment Date: |  |  | None
T&MRL Assessment
Dome
# | MRL Matrix Evaluation Threads | # | MRL Matrix Sub-Thread | Baseline | Current | Rationale (For Most Recent Assessment)
Technology Readiness Level (TRL)
A | Technology & Industrial Base | A1 | Technology Transition to Production
|  | A2 | Manufacturing Technology Development
B | Design | B1 | Producibility Program
|  | B2 | Design Maturity
C | Cost & Funding | C1 | Production Cost Knowledge (Cost Modeling)
|  | C2 | Cost Analysis
|  | C3 | Manufacturing Investment Budget
D | Materials | D1 | Maturity
|  | D2 | Availability
|  | D3 | Supply Chain Management
|  | D4 | Special Handling
E | Process Capability & Control | E1 | Modeling & Simulation (Product & Process)
|  | E2 | Manufacturing Process Maturity
|  | E3 | Process Yields & Rates
F | Quality Management | F1 | Quality Management Including Supplier Quality
G | Manufacturing Personnel | G1 | Manufacturing Personnel
H | Facilities | H1 | Tooling & Special Test & Inspection Equipment
|  | H2 | Facilities
I | Manufacturing Management | I1 | Manufacturing Planning & Scheduling
|  | I2 | Materials Planning
|  |  | Baseline MRL (excludes TRL): | -
|  |  | Current MRL (excludes TRL): |  | -
|  |  | High MRL (excludes TRL): | 0 | 0
|  |  | Low MRL (excludes TRL): | 0 | 0
|  |  | Average MRL (excludes TRL): | #DIV/0! | #DIV/0!
TRL Assessment Date:
MRL Assessment Date:
Special Instructions:
- Input to Blue shaded cells only
- TRLs and MRLs must be input as a whole number between 1 & 10 only otherwise leave blank (do not use 0)
- Provide Acronym for the technology being assessed, this will auto-fill the Acronym fields in the Single
"Maturity Plan" worksheet; input "Baseline" TRLs & MRLs by MRL Matrix Sub-Thread; subsequent Assessments to be input to
"Current" column
- Do not move or delete any rows, columns or cells or this workbook will not work properly.
- See embedded comment in cell D28 "Manufacturing Process Maturity"
- Rationale should be stated in terms of facts, data, artifacts, observations, etc. directly related to the current assessment, to lend credibility
to the selected MRL. Rationale should not be merely a restatement or rewording of the MRL Matrix exit criteria...be more specific.
Note on E13: Maximum 15 characters including spaces
Note on G16: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G17: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G18: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G19: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G20: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G21: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G22: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G23: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G24: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G25: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G26: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G27: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on D28: Use "Manufacturing Process Maturity" Spreadsheet to determine MRLs
Note on G28: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G29: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G30: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G31: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G32: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G33: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G34: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on G35: Try to avoid simply restating the MRL Matrix exit criteria as rationale. Instead, provide specific facts, data, artifacts, observations, test results, etc. that have been offered as proof for the MRL…this will lend credibility to your assessed MRL.
Note on E44: Date format = mm/yy example: June 2009 = 06/09
Note on F44: Date format = mm/yy example: June 2009 = 06/09
Note on E45: Date format = mm/yy example: June 2009 = 06/09
Note on F45: Date format = mm/yy example: June 2009 = 06/09

## Mfg'g Process Maturity
Manufacturing Process Maturity
Program: |  | example: HyperSonic Missile Program
Product Description: |  | example: Missile Seeker
Product Development Phase: |  | Technology Development
Transition Readiness Goals: |  | 6
T&MRL Valuation Method: |  | Lowest T&MRL Values
Most Recent Assessment Date: |  | None
Dome
Process / Step | Is This Process New? | Process Documentation in Place | Process Controls in Place | Current Drawing/Spec Revision | Product Specific Tooling/Fixturing in Place | MRL Level | Comments
Assembly
Step 1
Step 2
Step N
Test
Step 1
Step 2
Step N
Mechanical
ICD Conformance
[5 empty] | Composite MRL: | -
Special Instructions:
- Input to Blue shaded cells only
- Acronym will auto-fill from "Single T&MRL Assessment" worksheet
- Do not move or delete any rows, columns or cells or this workbook will not work
properly.
- You can add rows if necessary, either between Steps 2 and Steps N or above
ICD Conformance lines to ensure that the Composite MRL formula auto adjusts properly.
- Transfer the Composite MRL below to "Baseline MRL" sub-thread #14
"Manufacturing Process Maturity" in the "Single T&MRL Assessments" worksheet; update
the worksheet over time for "Current MRL"

## Maturity Plan
Single Technology TRL & MRL Maturity Planning Sheet
| Program: |  | example: HyperSonic Missile Program
| Product Description: |  | example: Missile Seeker
| Product Development Phase: |  | Technology Development
| Transition Readiness Goals: |  | 6
| T&MRL Valuation Method: |  | Lowest T&MRL Values
|  | Key Technology Assessed: |  | Acronym: | Dome
Technology Readiness Level - TRL
| Item # | Task Description | Rationale/Evidence/Risks to Completion | Responsible POC | Plan Due Date | Complete Date | TRL Act'l Increase | Funding Req'mts | Funding Type | Funded (Y/N) | TRL Base Plan | TRL Act'l
| 1 | Baseline TRL | [8 empty] | 0 | 0
| 1.01 | [10 empty] | 0
| 1.02 | [10 empty] | 0
| 1.03 | [10 empty] | 0
| 1.04 | [10 empty] | 0
| 1.05 | [10 empty] | 0
| 1.06 | [10 empty] | 0
| 1.07 | [10 empty] | 0
| 1.08 | [10 empty] | 0
| 1.09 | [10 empty] | 0
| 1.1 | [10 empty] | 0
| 1.11 | [10 empty] | 0
| 1.12 | [10 empty] | 0
| 1.13 | [10 empty] | 0
| 1.14 | [10 empty] | 0
| 1.15 | [10 empty] | 0
| 1.16 | [10 empty] | 0
| 1.17 | [10 empty] | 0
| 1.18 | [10 empty] | 0
| 1.19 | [10 empty] | 0
| 1.2 | [10 empty] | 0
[7 empty] | TRL funding plan: | 0 |  |  | Current TRL | 0
[7 empty] | Funded: | 0 |  | TRL Plan Complete? | N
[7 empty] | Unfunded: | 0 |  | In Risk Register?
Manufacturing Readiness Level - MRL
| Item # | Task Description | Rationale/Evidence/Risks to Completion | Responsible POC | Plan Due Date | Complete Date | MRL Act'l Increase | Funding Req'mts | Funding Type | Funded (Y/N) | MRL Base Plan | MRL Act'l
| 1 | Baseline MRL | [8 empty] | 0 | 0
| 1.01 | [10 empty] | 0
| 1.02 | [10 empty] | 0
| 1.03 | [10 empty] | 0
| 1.04 | [10 empty] | 0
| 1.05 | [10 empty] | 0
| 1.06 | [10 empty] | 0
| 1.07 | [10 empty] | 0
| 1.08 | [10 empty] | 0
| 1.09 | [10 empty] | 0
| 1.1 | [10 empty] | 0
| 1.11 | [10 empty] | 0
| 1.12 | [10 empty] | 0
| 1.13 | [10 empty] | 0
| 1.14 | [10 empty] | 0
| 1.15 | [10 empty] | 0
| 1.16 | [10 empty] | 0
| 1.17 | [10 empty] | 0
| 1.18 | [10 empty] | 0
| 1.19 | [10 empty] | 0
| 1.2 | [10 empty] | 0
[7 empty] | MRL funding plan: | 0 |  |  | Current MRL | 0
[7 empty] | Funded: | 0 |  | MRL Plan Complete? | N
[7 empty] | Unfunded: | 0 |  | In Risk Register?
Special Instructions:
- Input to Blue shaded cells only
- Acronym is the only field that will auto fill from "Single T&MRL
Assessment" worksheet…you need to manually transfer dates, TRLs and
MRLs from the "Single T&MRL Assessment" worksheet
- Do not move or delete any rows, columns or cells
or this workbook will not work properly.
Note on L15: Manually input TRL Plan in this column
Note on M15: Automatically generated to match TRL Plan. Subsequent lines are populated as a result of your input to column H "TRL Increase." Please review comments in first row under "TRL Increase"
Note on F16: Date format = mm/yy example: June 2009 = 06/09
Note on G16: Date format = mm/yy example: June 2009 = 06/09
Note on H16: Input a whole number between 1 & 9. This will result in an increase in the "TRL Actual" by that value. In the case of a completed action item that "cut-in" a new, less mature technology or process, you may need to decrease the "TRL Actual" to date to account for the "hit" to overall technology maturity. This would require you to input a negative number in this column that is large enough to reduce the "TRL Actual" column down to its new level
Note on I16: Input whole numbers only (i.e. 100, 50, 22, etc.), the worksheet will auto format to $K
Note on J16: Funding types include: - Contract - Capital - IR&D - ManTech - M&PE - Overhead - SBIR - Other
Note on K16: Must be capital "Y" or "N" only
Note on L37: "Y" for yes; "N" for no only
Note on L38: "Y" for yes; "N" for no only
Note on G42: Date format = mm/yy example: June 2009 = 06/09
Note on L42: Manually input MRL Plan in this column
Note on M42: Automatically generated to match MRL Plan. Subsequent lines are populated as a result of your input to column H "MRL Increase." Please review comments in first row under "MRL Increase"
Note on F43: Date format = mm/yy example: June 2009 = 06/09
Note on H43: Input a whole number between 1 & 9. This will result in an increase in the "MRL Actual" column by that value. In the case of a completed action item that "cut-in" a new, less mature technology or process, you may need to decrease the "MRL Actual" to date to account for the "hit" to this evaluation criteria's maturity. This would require you to input a negative number in this column that is large enough to reduce the "MRL Actual" column down to its new level
Note on I43: Input whole numbers only (i.e. 100, 50, 22, etc.), the worksheet will auto format to $K
Note on J43: Funding types include: - Contract - Capital - IR&D - ManTech - M&PE - Overhead - SBIR - Other
Note on K43: Must be capital "Y" or "N" only
Note on L64: "Y" for yes; "N" for no only
Note on L65: "Y" for yes; "N" for no only

## MRL Matrix Rev 11
Version 11 | 2011-05-01 | This version of the Criteria Matrix Matches the MRL Deskbook V2, May, 2011
DoD Manufacturing Readiness Levels (MRLs)
Acquisition Phase |  | Pre Materiel Solution Analysis (Pre MSA) |  |  | Materiel Solution Analysis (MSA) | Technology Development (TD) |  | Engineering & Mfg Development (EMD) |  | Low-Rate Initial Production (LRIP) | Full-Rate Production (FRP)
Technical Reviews |  |  |  |  | ASR | SRR/SFR | PDR | CDR | PRR/SVR | PCA
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
| Technology Maturity | Should be assessed at TRL 1. | Should be assessed at TRL 2. | Should be assessed at TRL 3. | Should be assessed at TRL 4. | Should be assessed at TRL 5. | Should be assessed at TRL 6. | Should be assessed at TRL 7 | Should be assessed at TRL 7. | Should be assessed at TRL 9. | Should be assessed at TRL 9.
A- Technology and Industrial Base | A.1 - Industrial base |  |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes. | Industrial base assessment initiated to identify potential manufacturing sources. Sole/single/foreign source vendors have been identified and planning has begun to minimize risks. | Industrial Capability Assessment (ICA) for MS B has been completed. Industrial capability in place to support mfg of development articles. Plans to minimize sole/foreign sources complete. Need for sole/single/foreign sources justified. Potential alternative sources identified. | Industrial capability to support production has been analyzed. Sole/single/foreign sources stability is assessed/monitored. Developing potential alternate sources as necessary. | Industrial Capability Assessment (ICA) for MS C has been completed. Industrial capability is in place to support LRIP. Sources are available, multi-sourcing where cost-effective or necessary to mitigate risk. | Industrial capability is in place to support start of FRP. | Industrial capability supports FRP. Industrial capability assessed to support modifications, upgrades, surge and other potential manufacturing requirements.
| A.2 - Manufacturing Technology Development |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Mfg Science & Advanced Mfg Technology requirements identified | Required manufacturing technology development efforts initiated, if applicable. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production relevant environment. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production representative environment. | Primary manufacturing technology efforts concluding, and some improvement efforts continuing. Required manufacturing technology solutions validated on a pilot line. | Manufacturing technology process improvements efforts initiated for FRP. | Manufacturing technology continuous process improvements ongoing.
B - Design | B.1 - Producibility Program |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Technology Development Strategy key components/ technologies. | Producibility and manufacturability assessments of key technologies and components initiated as appropriate. Ongoing design trades consider manufacturing processes and industrial base capability constraints. Manufacturing processes assessed for capability to test and verify in production, and influence on Operations & Support. | Producibility assessments and producibility trade studies (performance vs. producibility) of key technologies/components completed. Results used to shape Acquisition Strategy, Systems Engineering Plan (SEP), Manufacturing and Producibility plans, and planning for EMD or technology insertion programs. Preliminary design choices assessed against manufacturing processes and industrial base capability constraints. Producibility enhancement efforts (e.g. Design For Mfg, Assembly, Etc. (DFX)) initiated. | Detailed producibility trade studies using knowledge of key design characteristics and related manufacturing process capability completed. Producibility enhancement efforts (e.g. DFX) ongoing for optimized integrated system. Manufacturing processes re-assessed as needed for capability to test and verify potential influence on Operations & Support. | Producibility improvements implemented on system. Known producibility issues have been resolved and pose no significant risk for LRIP. | Prior producibility improvements analyzed for effectiveness during LRIP. Producibility issues/risks discovered in LRIP have been mitigated and pose no significant risk for FRP. | Design producibility improvements demonstrated in FRP. Process producibility improvements ongoing. All modifications, upgrades, Diminishing Mfg Sources & Material Shortages (DMSMS) and other changes assessed for producibility.
| B.2 - Design Maturity | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Draft Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred system concepts. | Lower level performance requirements sufficient to proceed to preliminary design. All enabling/critical technologies and components identified and considers the product lifecycle. Evaluation of design Key Characteristics (KC) initiated. Product data required for prototype component manufacturing released. | System allocated baseline established. Product requirements and features are well enough defined to support preliminary design review. Product data essential for subsystem/system prototyping has been released. Preliminary design KCs have been identified and mitigation plan in development. | Product design and features are well enough defined to support critical design review, even though design change traffic may be significant. All product data essential for component manufacturing has been released. Potential KC risk issues have been identified and mitigation plan is in place. | Detailed design of product features and interfaces is complete. All product data essential for system manufacturing has been released. Design change traffic does not significantly impact LRIP. Key Characteristics are attainable based upon pilot line demonstrations. | Major product design features and configuration are stable. System design has been validated through operational testing of LRIP items. Physical Configuration Audit (PCA) or equivalent complete as necessary. Design change traffic is limited. All KCs are controlled in LRIP to appropriate quality levels. | Product design is stable. Design changes are few and generally limited to those required for continuous improvement or in reaction to obsolescence. All KCs are controlled in FRP to appropriate quality levels.
C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling) |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified. | Prototype components produced in a production relevant environment, or simulations drive end-to-end cost models. Cost model includes materials, labor, equipment, tooling/Special Test Equipment (STE), setup, yield/scrap/rework, Work In Progress (WIP), and capability/capacity constraints. | Cost model updated with design requirements, material specifications, tolerances, integrated master schedule, results of system/subsystem simulations and production relevant prototype demonstrations. | Cost model updated with the results of systems/sub-systems produced in a production representative environment, production plant layout and design, and obsolescence solutions. | Cost models updated with results of pilot line build. | FRP cost model updated with result of LRIP build. | Cost model validated against actual FRP cost.
| C.2 - Cost Analysis | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR). | Costs analyzed using prototype component actuals to ensure target costs are achievable. Decisions regarding design choices, make/buy, capacity, process capability, sources, quality, key characteristics, yield/rate, and variability influenced by cost models. | Costs analyzed using prototype system/sub-system actuals to ensure target costs are achievable. Allocate cost targets to subsystems. Cost reduction and avoidance strategies developed. Provide manufacturing cost drivers for "Should-Cost" models. | Manufacturing costs rolled up to system/sub-system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction and avoidance strategies underway. Update manufacturing cost drivers for "Should-Cost" models. | Costs analyzed using pilot line actuals to ensure target costs are achievable. Manufacturing cost analysis supports proposed changes to requirements or configuration. Cost reduction initiatives ongoing. Update manufacturing cost drivers for "Should-Cost" models. | LRIP cost goals met and learning curve analyzed with actual data. Cost reduction initiatives ongoing. Touch labor efficiency analyzed to meet production rates and elements of inefficiency are identified with plans in place for reduction. | FRP cost goals met. Cost reduction initiatives ongoing.
| C.3 - Manufacturing Investment Budget | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 6 by MS B. All outstanding MRL 5 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 8 by MS C. Estimate includes capital investment for production-representative equipment by CDR and pilot line equipment by MS C. All outstanding MRL 6 risk areas understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 8 by MS C. All outstanding MRL 7 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for LRIP and FRP. All outstanding MRL 8 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for FRP. All outstanding MRL 9 risk areas understood with approved mitigation plans in place. | Production budgets sufficient for production at required rates and schedule to support funded program.
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.1 - Maturity | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment. | Materials have been manufactured or produced in a prototype environment (may be in a similar application/program). Maturation efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place and material properties have been adequately characterized. | Material maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated during EMD as adequate to support LRIP. Material specification stable. | Material is controlled to specification in LRIP. Materials proven and validated as adequate to support FRP. | Material is controlled to specification in FRP.
| D.2 - Availability |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated. | Availability issues addressed for prototype build. Significant material risks identified for all materials. Planning has begun to address scale-up issues. | Availability issues addressed to meet EMD build. Long lead items identified. Potential obsolescence issues identified. | Availability issues addressed to meet LRIP builds. Long lead procurement identified and mitigated. Obsolescence plan in place. | Long lead procurement initiated for LRIP. Availability issues pose no significant risk for LRIP. Availability issues addressed to meet FRP builds. | Long lead procurement initiated for FRP. Availability issues pose no significant risk for FRP. | Program is in FRP with no significant material availability issues.
| D.3 - Supply Chain Management |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources. | Potential supply chain sources identified and evaluated as able to support prototype build. | Supply chain plans in place (e.g. teaming agreements, etc.) supporting an EMD contract award. | Effective supply chain management process in place. Assessment of critical first tier supply chain completed. | Supply chain adequate to support LRIP. Assessment of critical second and lower tier supply chain completed. | Supply chain is stable and adequate to support FRP. Long term agreements in place where practical. | Supply chain proven and supports FRP requirements.
| D.4 - Special Handling (i.e. Government Furnished Property (GFP), shelf life, security, hazardous materials, storage environment, etc.) |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified. | Special handling procedures applied in production relevant environment. Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. | Special handling procedures applied in production relevant environment. Plans to address special handling requirement gaps complete. | Special handling procedures applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. | Special handling procedures applied in pilot line environment. Special handling procedures demonstrated in EMD or Technology Insertion Programs. Special handling issues pose no significant risk for LRIP. All work instructions contain special handling provisions as required. | Special handling procedures applied in LRIP environment. Special handling procedures demonstrated in LRIP. Special handling issues pose no significant risk for FRP. | Special handling procedures effectively implemented in FRP.
E - -Process Capability & Control | E.1 - Modeling & Simulation (Product & Process) |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified. | Initial model/simulation (product or process) developed at the component level and used to determine constraints. | Initial model/simulation developed at the sub-system or system level, and used to determine system constraints. | Model/simulation used to determine system constraints and identify improvement opportunities. | Model/simulation verified by pilot line build. Results used to improve process and determine that LRIP requirements can be met. | Model/simulation verified by LRIP build, assists in management of LRIP, and determines that FRP requirements can be met. | Model/simulation verified by FRP build. Production simulation models used as a tool to assist in management of FRP.
| E.2 - Manufacturing Process Maturity |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes. | Maturity has been assessed on similar processes in production. Process capability requirements have been identified for pilot line, LRIP and FRP. | Manufacturing processes demonstrated in production relevant environment. Collection or estimation of process capability data from prototype build has begun. Process capability requirements refined. | Manufacturing processes demonstrated in a production representative environment. Continue collecting or estimating process capability data. Process capability requirements refined. | Manufacturing processes verified for LRIP on a pilot line. Process Capability data from pilot line meets target. Process capability requirements refined. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program LRIP objectives. Variability experiments conducted to show FRP impact and potential for continuous improvement. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program FRP objectives.
| E.3 - Process Yields and Rates |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA). | Target yields and rates established for pilot line, LRIP, and FRP. Yield and rate issues identified. Improvement plans developed/initiated. | Yields and rates from production relevant environment evaluated against targets and the results feed improvement plan. | Yields and rates from production representative environment evaluated against pilot line targets and the results feed improvement plans. | Pilot line targets achieved. Yields and rates required to begin LRIP refined using pilot line results. Improvement plans ongoing and updated. | LRIP yield and rate targets achieved. Yields and rates required to begin FRP refined using LRIP results. Yield improvements on-going. | FRP yield and rate targets achieved. Yield improvements on-going.
F - Quality Management | F.1 - Quality Management including Supplier Quality. |  |  |  | Quality strategy identified as part of the Technology Development Strategy and included in Systems Engineering Plan (SEP). | Quality strategy updated to reflect Key Characteristic identification activities. | Initial quality plan and quality management system is in place. Quality risks and metrics have been identified and improvement plans initiated. Key Characteristic management approach defined. | Quality targets established. Quality data from the production representative environment collected and analyzed and results used to shape improvement plans. | Quality targets assessed against pilot line, results feed continuous quality improvements. Supplier products have completed qualification testing and first article inspection. Acceptance testing of supplier products is adequate to begin LRIP. Key Characteristics managed. | Quality targets verified on LRIP line. Continuous quality improvement on-going. Acceptance testing of supplier products is adequate to begin FRP. Key Characteristics managed in LRIP. | Quality targets verified on FRP line. Continuous quality improvement on-going.
G - Mfg Workforce (Engineering & Production) | G.1 - Mfg Workforce (Engineering & Production) |  |  | New manufacturing skills identified. | Mfg skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Availability of process development workforce for the Technology Development Phase is determined. | Skill sets identified and plans developed to meet prototype and production needs. Special skills certification and training requirements established. | Mfg workforce skills available for production in a relevant environment. Identify resources (quantities and skill sets) and develop initial plans to achieve requirements for pilot line and production. | Mfg workforce resource requirements identified for pilot line. Plans developed to achieve pilot line requirements. Plans updated to achieve LRIP workforce requirements. Pilot line workforce trained in production representative environment. | Mfg workforce resource requirements identified for LRIP. Plans developed to achieve LRIP requirements. Plans updated to achieve FRP workforce requirements. LRIP personnel trained on pilot line where possible. | LRIP personnel requirements met. Implement plan to achieve FRP workforce requirements. | FRP personnel requirements met. Production workforce skill sets maintained in response to attrition of workforce.
H - Facilities | H.1 - Tooling / Special Test and Inspection Equipment (STE/SIE) |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA. | Identify tooling and STE/SIE requirements and provide supporting rationale and schedule. | Prototype tooling and STE/SIE concepts demonstrated in production relevant environment. Production tooling and STE/SIE requirements developed. | Production tooling and STE/SIE design and development efforts underway. Mfg equipment maintenance strategy developed. | Tooling, test and inspection equipment proven on pilot line and additional requirements identified for LRIP. Mfg equipment maintenance demonstrated on pilot line. | All tooling, test and inspection equipment proven in LRIP and requirements identified for FRP. Mfg equipment maintenance schedule demonstrated. | Proven tooling, test and inspection equipment in place to support maximum FRP. Planned equipment maintenance schedule achieved.
| H.2 - Facilities |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA. | Manufacturing facilities identified and plans developed to produce prototypes. | Manufacturing facilities identified and plans developed to produce pilot line build. | Manufacturing facilities identified and plans developed to produce LRIP build. | Pilot line facilities demonstrated. Mfg facilities adequate to begin LRIP. Plans in place to support transition to FRP. | Mfg facilities in place and demonstrated in LRIP. Capacity plans adequate to support FRP. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements.
I - Mfg Management | I.1 - Mfg Planning & Scheduling |  |  |  | Mfg strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Technology Development Strategy (TDS). | Mfg strategy refined based upon preferred concept. Prototype schedule risk mitigation efforts initiated. | Initial mfg approach developed. All system design related mfg events included in Integrated Master Plan/Schedule (IMP/IMS). Mfg risk mitigation approach for pilot line or technology insertion programs defined. | Initial mfg plan developed. Mfg planning included in IMP/IMS. Mfg risks integrated into risk mitigation plans. Develop initial work instructions. Effective production control system in place to support pilot line. | Mfg plan updated for LRIP. All key manufacturing risks are identified and assessed with approved mitigation plans in place. Work instructions finalized. Effective production control system in place to support LRIP. | Mfg plan updated for FRP. All manufacturing risks tracked and mitigated. Effective production control system in place to support FRP. | All manufacturing risks mitigated.
| I.2 - Materials Planning |  |  |  | Technology development article component list developed with associated lead time estimates. | Technology development part list maturing, Make/buy evaluations begin, and include production considerations reflecting Pilot line, LRIP, and FRP needs. Lead times and other risks identified. | Most material decisions complete (make/buy), material risks identified and mitigation plans developed. Bill of Materials (BOM) initiated. | Make/Buy decisions and BOM complete for pilot line build. Material planning systems in place for pilot line build. | Make/Buy decisions and BOM complete to support LRIP. Material planning systems proven on pilot line for LRIP build. | Make/Buy decisions and BOM complete to support FRP. Material planning systems proven in LRIP and sufficient for FRP. | Material planning systems validated on FRP build.
For explanation of Production Relevant Environment, Production Representative Environment, and Pilot Line Environment see the DoD MRL Deskbook.
A
FRP
C
B

## MRL Definitions
MANUFACTURING READINESS LEVEL DEFINITIONS
There are ten MRLs (numbered 1 through 10) that are correlated to the
nine TRLs in use. The final level (MRL 10) measures aspects of lean practices
and continuous improvement for systems in production.
MRL 1: Basic Manufacturing Implications Identified
This is the lowest level of manufacturing readiness. The focus is to
address manufacturing shortfalls and opportunities needed to achieve
program objectives. Basic research (i.e., funded by budget activity)
begins in the form of studies.
MRL 2: Manufacturing Concepts Identified
This level is characterized by describing the application of new
manufacturing concepts. Applied research (i.e., funded by budget activity
6.2) translates basic research into solutions for broadly defined military
needs. Typically this level of readiness in the S&T environment includes
identification, paper studies and analysis of material and process
approaches. An understanding of manufacturing feasibility and risk is
emerging.
MRL 3: Manufacturing Proof of Concept Developed
This level begins the validation of the manufacturing concepts
through analytical or laboratory experiments. This level of readiness is
typical of technologies in the S&T funding categories of Applied Research
and Advanced Development (i.e., funded by budget activity 6.3). Materials
and/or processes have been characterized for manufacturability and
availability but further evaluation and demonstration is required.
Experimental hardware models have been developed in a laboratory
environment that may possess limited functionality.
MRL 4: Capability to produce the technology in a laboratory
environment
This level of readiness is typical for S&T Programs in the budget
activity 6.2 and 6.3 categories and acts as an exit criterion for the Materiel
Solution Analysis (MSA) Phase approaching a Milestone A decision.
Technologies should have matured to at least TRL 4. This level indicates
that the technologies are ready for the Technology Development Phase of
acquisition. At this point, required investments, such as manufacturing
technology development, have been identified. Processes to ensure
manufacturability, producibility, and quality are in place and are sufficient
to produce technology demonstrators. Manufacturing risks have been
identified for building prototypes and mitigation plans are in place. Target
cost objectives have been established and manufacturing cost drivers
have been identified. Producibility assessments of design concepts have
been completed. Key design performance parameters have been
identified as well as any special tooling, facilities, material handling and
skills required.
MRL 5: Capability to produce prototype components in a production
relevant environment
This level of maturity is typical of the mid-point in the Technology
Development Phase of acquisition, or in the case of key technologies,
near the mid-point of an Advanced Technology Demonstration (ATD)
project. Technologies should have matured to at least TRL 5. The
industrial base has been assessed to identify potential manufacturing
sources. A manufacturing strategy has been refined and integrated with
the risk management plan. Identification of enabling/critical technologies
and components is complete. Prototype materials, tooling and test
equipment, as well as personnel skills have been demonstrated on
components in a production relevant environment, but many
manufacturing processes and procedures are still in development.
Manufacturing technology development efforts have been initiated or are
ongoing. Producibility assessments of key technologies and components
are ongoing. A cost model has been constructed to assess projected
manufacturing cost.
MRL 6: Capability to produce a prototype system or subsystem in a
production relevant environment
This MRL is associated with readiness for a Milestone B decision to
initiate an acquisition program by entering into the Engineering and
Manufacturing Development (EMD) Phase of acquisition. Technologies
should have matured to at least TRL 6. It is normally seen as the level of
manufacturing readiness that denotes completion of S&T development
and acceptance into a preliminary system design. An initial manufacturing
approach has been developed. The majority of manufacturing processes
have been defined and characterized, but there are still significant
engineering and/or design changes in the system itself. However,
preliminary design of critical components has been completed and
producibility assessments of key technologies are complete. Prototype
materials, tooling and test equipment, as well as personnel skills have
been demonstrated on systems and/or subsystems in a production
relevant environment. A cost analysis has been performed to assess
projected manufacturing cost versus target cost objectives and the
program has in place appropriate risk reduction to achieve cost
requirements or establish a new baseline. This analysis should include
design trades. Producibility considerations have shaped system
development plans. The Industrial Capabilities Assessment (ICA) for
Milestone B has been completed. Long-lead and key supply chain
elements have been identified.
MRL 7: Capability to produce systems, subsystems, or components
in a production representative environment
This level of manufacturing readiness is typical for the mid-point of
the Engineering and Manufacturing Development (EMD) Phase leading to
the Post-CDR Assessment. Technologies should be on a path to achieve
TRL 7. System detailed design activity is underway. Material
specifications have been approved and materials are available to meet the
planned pilot line build schedule. Manufacturing processes and
procedures have been demonstrated in a production representative
environment. Detailed producibility trade studies and risk assessments
are underway. The cost model has been updated with detailed designs,
rolled up to system level, and tracked against allocated targets. Unit cost
reduction efforts have been prioritized and are underway. The supply
chain and supplier quality assurance have been assessed and long-lead
procurement plans are in place. Production tooling and test equipment
design and development have been initiated.
MRL 8: Pilot line capability demonstrated; Ready to begin Low Rate
Initial Production
This level is associated with readiness for a Milestone C decision,
and entry into Low Rate Initial Production (LRIP). Technologies should
have matured to at least TRL 7. Detailed system design is essentially
complete and sufficiently stable to enter low rate production. All materials
are available to meet the planned low rate production schedule.
Manufacturing and quality processes and procedures have been proven in
a pilot line environment and are under control and ready for low rate
production. Known producibility risks pose no significant challenges for
low rate production. The engineering cost model is driven by detailed
design and has been validated with actual data. The Industrial
Capabilities Assessment for Milestone C has been completed and shows
that the supply chain is established and stable.
MRL 9: Low rate production demonstrated; Capability in place to
begin Full Rate Production
At this level, the system, component or item has been previously
produced, is in production, or has successfully achieved low rate initial
production. Technologies should have matured to TRL 9. This level of
readiness is normally associated with readiness for entry into Full Rate
Production (FRP). All systems engineering/design requirements should
have been met such that there are minimal system changes. Major
system design features are stable and have been proven in test and
evaluation. Materials are available to meet planned rate production
schedules. Manufacturing process capability in a low rate production
environment is at an appropriate quality level to meet design key
characteristic tolerances. Production risk monitoring is ongoing. LRIP
cost targets have been met, and learning curves have been analyzed with
actual data. The cost model has been developed for FRP environment
and reflects the impact of continuous improvement.
MRL 10: Full Rate Production demonstrated and lean production
practices in place
This is the highest level of production readiness. Technologies should
have matured to TRL 9. This level of manufacturing is normally
associated with the Production or Sustainment phases of the acquisition
life cycle. Engineering/design changes are few and generally limited to
quality and cost improvements. System, components or items are in full
rate production and meet all engineering, performance, quality and
reliability requirements. Manufacturing process capability is at the
appropriate quality level. All materials, tooling, inspection and test
equipment, facilities and manpower are in place and have met full rate
production requirements. Rate production unit costs meet goals, and
funding is sufficient for production at required rates. Lean practices are
well established and continuous process improvements are ongoing.
Although the MRLs are numbered, the numbers themselves are
unimportant. The numbers represent a non-linear ordinal scale that identifies
what maturity should be as a function of where a program is in the acquisition life
cycle (as described in Section 3). Using numbers is simply a convenient naming
convention.

## MRL Definition of Terms
2.4 DEFINITION OF TERMS
As manufacturing readiness increases, demonstration of manufacturing
capabilities should be accomplished in more realistic environments.
Prior to Milestone A, the MRLs focus on manufacturing feasibility by identifying and
reducing the production risk of the proposed concepts. These proposed
technology concepts are generally demonstrated in a laboratory environment.
MRLs focus on identifying manufacturing challenges that should be addressed in
the TD phase.
Prior to Milestone B, MRLs focus on a contractor’s capability to produce
prototypes in a production relevant environment, outside of the laboratory. The
parameters defining a production relevant environment should be based on the
risks and uniqueness associated with demonstrating that contractors’ key
processes meet program requirements.
A production relevant environment represents the manufacturing capability
needed to proceed into the EMD Phase with high confidence of achieving
program cost, schedule and performance requirements. This level of production
realism is well beyond what is seen in a laboratory. The emphasis is on
addressing higher risk areas (e.g. more advanced technologies and newer
manufacturing capabilities). During this critical junction it is essential that the
contractor(s) demonstrate the capability to build the product or a similar product
(e.g. size, tolerances, quality levels, processes, and testing) in the facility
intended to be used during production.
Production relevant environment—An environment with some shop
floor production realism present (such as facilities, personnel, tooling,
processes, materials etc.). There should be minimum reliance on
laboratory resources during this phase. Demonstration in a production
relevant environment implies that contractor(s) must demonstrate their
ability to meet the cost, schedule, and performance requirements of the
EMD Phase based on their production of prototypes. The demonstration
must provide the program with confidence that these targets will be
achieved. Furthermore, there must be an indication of how the
contractor(s) intend to achieve the requirements in a production
representative and pilot environments.
As a program evolves through the EMD phase and hardware is built for
qualification testing, the manufacturing processes should become more robust
and mature to address production representative activities on the whole program.
Production representative environment—An environment that has as
much production realism as possible, considering the maturity of the
design. Production personnel, equipment, processes, and materials that
will be present on the pilot line should be used whenever possible. The
work instructions and tooling should be of high quality, and the only
changes anticipated on these items are associated with design changes
downstream that address performance or production rate issues. There
should be no reliance on a laboratory environment or personnel.
The final stage of EMD is producing products that look and operate like
they are production units from LRIP. These units need to be built on a pilot
production line to adequately demonstrate the ability to migrate from EMD to
LRIP. Without this realism it would be very difficult to obtain confidence that the
production process will be able to meet cost, schedule, and performance (e.g.
quality) requirements for production.
Pilot line environment—An environment that incorporates all of the key
production realism elements (equipment, personnel skill levels, facilities,
materials, components, work instructions, processes, tooling, temperature,
cleanliness, lighting etc.) required to manufacture production configuration
items, subsystems or systems that meet design requirements in low rate
production. To the maximum extent practical, the pilot line should utilize
full rate production processes.
The definitions of relevant, representative, and pilot line environments are
intended to demonstrate the natural progression of manufacturing maturity
throughout the acquisition life cycle. The program office and contractor must
reach agreement on the detailed production realism content (equipment,
personnel skill levels, processes, etc.) for each definition above. This agreement
must be based on the specific situation and its associated manufacturing risk in
order to mitigate that risk in a timely and thorough manner.
Two other definitions are germane to this discussion:
Manufacturability—The characteristics considered in the design cycle
that focus on process capabilities, machine or facility flexibility, and the
overall ability to consistently produce at the required level of cost and
quality. Associated activities may include some or all of the following:
- Design for commonality and standardization—fewer parts
- Perform comprehensive technology assessment, including
commercial industrial applications and the supplier base
- Design for multi-use and dual-use applications
- Design for modularity and plug compatible interface/integration
- Design for flexibility/adaptability or use “robust design”
- Utilize reliable processes and materials
- Utilize monolithic and determinant assembly
- Design for manufacturing and assembly
- Achieve production yield
Producibility—The relative ease of producing an item that meets
engineering, quality and affordability requirements.

## TRL Criteria
Hardware and Software Technology Readiness Levels (TRLs)
[Sources: Defense Acquisition Guidebook (October 2004) and IT TRL Working Group Minutes (November 2004)]
Hardware TRL Definitions, Descriptions, and Supporting Information |  |  | Software TRL Definitions, Descriptions, and Supporting Information
TRL Definition | Description | Supporting Information | TRL Definition | Description | Supporting Information
1 Basic principles observed and reported. | Lowest level of technology readiness. Scientific research begins to be translated into applied research and development (R&D). Examples might include paper studies of a technology’s basic properties. | Published research that identifies the principles that underlie this technology. References to who, where, when. | 1 Basic principles observed and reported. | Lowest level of software technology readiness. A new software domain is being investigated by the basic research community. This level extends to the development of basic use, basic properties of software architecture, mathematical formulations, and general algorithms. | Basic research activities, research articles, peer-reviewed white papers, point papers, early lab model of basic concept may be useful for substantiating the TRL level.
2 Technology concept and/or application formulated. | Invention begins. Once basic principles are observed, practical applications can be invented. Applications are speculative, and there may be no proof or detailed analysis to support the assumptions. Examples are limited to analytic studies. | Publications or other references that outline the application being considered and that provide analysis to support the concept. | 2 Technology concept and/or application formulated. | Once basic principles are observed, practical applications can be invented. Applications are speculative, and there may be no proof or detailed analysis to support the assumptions. Examples are limited to analytic studies using synthetic data. | Algorithms run on a surrogate processor in a laboratory environment, instrumented components operating in laboratory environment, laboratory results showing validation of critical properties.
3 Analytical and experimental critical function and/or characteristic proof of concept. | Active R&D is initiated. This includes analytical studies and laboratory studies to validate physically the analytical predictions of separate elements of the technology. Examples include components that are not yet integrated or representative. | Results of laboratory tests performed to measure parameters of interest and comparison to analytical predictions for critical subsystems. References to who, where, and when these tests and comparisons were performed. | 3 Analytical and experimental critical function and/or characteristic proof of concept. | Active R&D is initiated. The level at which scientific feasibility is demonstrated through analytical and laboratory studies. This level extends to the development of limited functionality environments to validate critical properties and analytical predictions using nonintegrated software components and partially representative data. | Algorithms run on a surrogate processor in a laboratory environment, instrumented components operating in laboratory environment, laboratory results showing validation of critical properties.
4 Component and/or breadboard validation in a laboratory environment. | Basic technological components are integrated to establish that they will work together. This is relatively “low fidelity” compared with the eventual system. Examples include integration of “ad hoc” hardware in the laboratory. | System concepts that have been considered and results from testing laboratory-scale breadboard(s). References to who did this work and when. Provide an estimate of how breadboard hardware and test results differ from the expected system goals. | 4 Module and/or subsystem validation in a laboratory environment (i.e., software prototype development environment). | Basic software components are integrated to establish that they will work together. They are relatively primitive with regard to efficiency and robustness compared with the eventual system. Architecture development initiated to include interoperability, reliability, maintainability, extensibility, scalability, and security issues. Emulation with current/legacy elements as appropriate. Prototypes developed to demonstrate different aspects of eventual system. | Advanced technology development, stand-alone prototype solving a synthetic full-scale problem, or standalone prototype processing fully representative data sets.
5 Component and/ or breadboard validation in a relevant environment. | Fidelity of breadboard technology increases significantly. The basic technological components are integrated with reasonably realistic supporting elements so they can be tested in a simulated environment. Examples include “high-fidelity” laboratory integration of components. | Results from testing a laboratory breadboard system are integrated with other supporting elements in a simulated operational environment. How does the “relevant environment” differ from the expected operational environment? How do the test results compare with expectations? What problems, if any, were encountered? Was the breadboard system refined to more nearly match the expected system goals? | 5 Module and/or subsystem validation in a relevant environment. | Level at which software technology is ready to start integration with existing systems. The prototype implementations conform to target environment/interfaces. Experiments with realistic problems. Simulated interfaces to existing systems. System software architecture established. Algorithms run on a processor(s) with characteristics expected in the operational environment. | System architecture diagram around technology element with critical performance requirements defined. Processor selection analysis, Simulation/Stimulation (Sim/Stim) Laboratory buildup plan. Software placed under configuration management. COTS/GOTS in the system software architecture are identified.
6 System/ subsystem model or prototype demonstration in a relevant environment. | Representative model or prototype system, which is well beyond that of TRL 5, is tested in a relevant environment. Represents a major step up in a technology’s demonstrated readiness. Examples include testing a prototype in a high-fidelity laboratory environment or in a simulated operational environment. | Results from laboratory testing of a prototype system that is near the desired configuration in terms of performance, weight, and volume. How did the test environment differ from the operational environment? Who performed the tests? How did the test compare with expectations? What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before moving to the next level? | 6 Module and/or subsystem validation in a relevant end-to-end environment. | Level at which the engineering feasibility of a software technology is demonstrated. This level extends to laboratory prototype implementations on full-scale realistic problems in which the software technology is partially integrated with existing hardware/software systems. | Results from laboratory testing of a prototype package that is near the desired configuration in terms of performance, including physical, logical, data, and security interfaces. Comparisons between tested environment and operational environment analytically understood. Analysis and test measurements quantifying contribution to system-wide requirements such as throughput, scalability, and reliability. Analysis of human-computer (user environment) begun.
7 System prototype demonstration in an operational environment. | Prototype near or at planned operational system. Represents a major step up from TRL 6 by requiring demonstration of an actual system prototype in an operational environment (e.g., in an aircraft, in a vehicle, or in space). Examples include testing the prototype in a test bed aircraft. | Results from testing a prototype system in an operational environment. Who performed the tests? How did the test compare with expectations? What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before moving to the next level? | 7 System prototype demonstration in an operational high-fidelity environment. | Level at which the program feasibility of a software technology is demonstrated. This level extends to operational environment prototype implementations where critical technical risk functionality is available for demonstration and a test in which the software technology is well integrated with operational hardware/software systems. | Critical technological properties are measured against requirements in a simulated operational environment.
8 Actual system completed and qualified through test and demonstration. | Technology has been proven to work in its final form and under expected conditions. In almost all cases, this TRL represents the end of true system development. Examples include developmental test and evaluation of the system in its intended weapon system to determine if it meets design specifications. | Results of testing the system in its final configuration under the expected range of environmental conditions in which it will be expected to operate. Assessment of whether it will meet its operational requirements. What problems, if any, were encountered? What are/were the plans, options, or actions to resolve problems before finalizing the design? | 8 Actual system completed and mission qualified through test and demonstration in an operational environment. | Level at which a software technology is fully integrated with operational hardware and software systems. Software development documentation is complete. All functionality tested in simulated and operational scenarios. | Published documentation and product technology refresh build schedule. Software resource reserve measured and tracked.
9 Actual system proven through successful mission operations. | Actual application of the technology in its final form and under mission conditions, such as those encountered in operational test and evaluation (OT&E). Examples include using the system under operational mission conditions. | OT&E reports. | 9 Actual system proven through successful mission-proven operational capabilities. | Level at which a software technology is readily repeatable and reusable. The software based on the technology is fully integrated with operational hardware/software systems. All software documentation verified. Successful operational experience. Sustaining software engineering support in place. Actual system. | Production configuration management reports. Technology integrated into a reuse “wizard”; out-year funding established for support activity

## TRL Definitions
TRL Definitions
DEFENSE ACQUISITION GUIDEBOOK
BREADBOARD | Integrated components that provide a representation of a system/subsystem and which can be used to determine concept feasibility and to develop technical data. Typically configured for laboratory use to demonstrate the technical principles of immediate interest. May resemble final system/subsystem in function only.
“HIGH FIDELITY” | Addresses form, fit and function. High-fidelity laboratory environment would involve testing with equipment that can simulate and validate all system specifications within a laboratory setting.
“LOW FIDELITY” | A representative of the component or system that has limited ability to provide anything but first order information about the end product. Low-fidelity assessments are used to provide trend analysis.
MODEL | A functional form of a system, generally reduced in scale, near or at operational specification. Models will be sufficiently hardened to allow demonstration of the technical and operational capabilities required of the final system.
OPERATIONAL ENVIRONMENT | Environment that addresses all of the operational requirements and specifications required of the final system to include platform/packaging.
PROTOTYPE | A physical or virtual model used to evaluate the technical or manufacturing feasibility or military utility of a particular technology or process, concept, end item or system.
RELEVANT ENVIRONMENT | Testing environment that simulates the key aspects of the operational environment.
SIMULATED OPERATIONAL ENVIRONMENTAL | Either 1) a real environment that can simulate all of the operational requirements and specifications required of the final system, or 2) a simulated environment that allows for testing of a virtual prototype; used in either case to determine whether a developmental system meets the operational requirements and specifications of the final system.